## Template
[5 empty] | Value | Approx. Story points
Epic | Story | Task | What need to do (shortly) | Estimation (Approximation) | XS
Epic №1 | Story 1 | task 1 |  | XS | S
|  | task 2 |  |  | M
| Story 2 | task 3 |  |  | L
XL
XXL

## Epics
Epic | Epic comment | Story | Task | What need to do (shortly)/RFC | Estimation (Approximation) | Assignee
We need one more meeting with Chris for the whole team
CDSPEG-24 - Send email requests to Sendgrid and handle responses | May be postponed for now (mocked) L by Chris | Setup Sendgrid environement | Test account (sub user) | RFC: If the Bluecore is similar, what is it there for? Different SendGrid implementtion. Irrelevant for this project. | S | EI
|  | Connect to SendGrid | API calls | Assign to Chris | S
|  |  | Error handling & logging | Maybe assigned to Chris | S
|  |  | Functional/integration tests | M, but can be S (assuming S is more than a day) to set up and then add new functionality on the go | M
|  |  | Performance test | Should be just a simple run after #26-#27 are done | XS |  | XS | up to 1 day | 1 | a day
[7 empty] | S | 1 - 2 days |  | a few days
CDSPEG-25 - Add Error handling and Metrics to SendGrid solution | May be postponed for now (mocked) L by Chris | Recovery logic |  |  | M | ? | M | 4-5 days |  | a week (half a sprint)
[7 empty] | L | 5-7 days | 8 | the whole sprint
|  | Metrics |  |  | M | ? | XL | not less thne 10 days |  | a month
[7 empty] | XXL | Epic, need decomposition |  | ...should not be here
CDSPEG-26 - Build the supporting framework to test the SendGrid and Observability features | M by Chris | Application deployment | <= | RFC: Deploy the application as an autoscaled, load balanced service - manually? CF template? Is there any specific requirements for a load balancer? Can be manual, no CF template Can we use Kubernetes right away? Yes, if it's not goimg to slow down the team | M | OG
|  | Configuration (?) | <= | Configurations to mock Kafka/etc Chris to provide an sample config | S | ?
|  | Create load generator | Create basic LG | RFC: are we using load generator for the queue only, or for Kafka as well ( https://confluence.nike.com/display/ICP/Project+Milestones, Load Generator section)? If yes, is it related to the same epic, or should be counted towards #28/#29? Only for the queue. Need to test both at same time, because Kafka is a side car for the Transporter | S | SF
|  |  | Configure LG |  | M | SF
|  |  | Operationalize LG (?) | RFC: Should load generator be deployed as well and operated remotely? Manaul or extreemly simple Agent. |  | ?
CDSPEG-27 - Perform string testing on the Sendgrid and Observability solutions | Cannot start without completing #26 first |  |  | RFC: How to measure performance (metrics/endpoints/check queue/etc)?
CDSPEG-28 - Notification Publisher - plugin translation layer for NSP (Nike Streaming Platform) requests | M by Chris | Plugin framework | Ability to add new plugins | XS if hardcoded RFC: definition of plugins Can be hardcoded/same as the sample code | XS | OH
|  |  | Ability to add new topics |  | S
|  |  | Storing schemas |  | S
|  | Data conversion | <= | Looks like data conversion\transformation is the core of the whole system. Implementation depends on requirements, but intensive testing required -> doubles required capacity The mapping is here: https://confluence.nike.com/display/ICP/Observability+MVP+Project | M
CDSPEG-29 - Notification Producer - Kafka Generic Record producer | L by Chris | Kafka producer | Basic producer | Could be stretched to M, depending on req | S | KS
|  |  | Producer configuration | https://confluence.nike.com/display/ICP/Notification+Producer+Configurations | XS | KS
|  | Error handling (see https://confluence.nike.com/pages/viewpage.action?pageId=376563896 ) |  | Observability errors: log, alert, send to QUEUE (RETRY, ORPHAN, or DLQ), a lot of logic/scenarios M or S RFC: If the call to sendgrid fails, it will still be recorded to Kafka. Should Notification producer/publisher push messages to RETRY queue or should it be done in MessageProcessor in the notifications-core? Chris to answer in Jira ticket | M | ?
|  | Metrics (see https://confluence.nike.com/display/ICP/Notification+Producer+Metrics ) | <= | Not clear how SignalFX work A lot more details required (found only one metric namely - count failed\rejected): 1. Should we implement custom or use provided cloud solutions? 2. How, where and by whom it should be accessible? Are there any special requirements to storing\handling of historical data? 3. Is there a need for alarms\triggers, if so - should it be user specified or predefined? 4. The same for data views - required? configurable? predefined? 5. Detailed descriprion with expected outputs per metric type very desirable Chris to answer in Jira ticket | M | OG
CDSPEG-30 - CDS Transporter Migration - Combined Nike code merge and integration | This looks like next sprint/iteration, because it requires all code to be ready to be merged with Nike env